## Bug Metric
Iteration | Number of Bugs | Number of Low Impact | Number of High Impact | Number of Critical Impact | Bug Metric | Action Done | Severity | Description
1 | 0 | 0 | 0 | 0 | 0 | Nil | Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
2 | 0 | 0 | 0 | 0 | 0 | Nil | High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
3 | 3 | 0 | 2 | 1 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project. | Critical Impact (10 points) | The system is down or is usable after a short period of time. We have to fix the bugs to continue.
4
5 | [6 empty] | Points Calculation: Total = 1 x num (low) + 5 x num (high) + 10 x num (critical)
6
7
8 | [6 empty] | Points in Iteration | Action
9 | [6 empty] | Points=<5 | Fix during buffer time only.
10 | [6 empty] | 5<Points<10 | Use the planned debugging time.
11 | [6 empty] | Points>=10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
12
13
14
15
Total | 3 | 0 | 2 | 1 | 20
Iteration

## Bug Log
No. | Iteration | Git Commit ID | Function | Description | Bug Metric Cause | Date Found | Who found? | Date Solved | Time Taken | Severity (Impact) | Points Allocation | Points Accumulated Per Iteration | Status | Action
1 | 3 |  | Registration | User unable to register new account even with the givern correct inputs. |  | 2018-10-20 | Li Kai |  |  | High | 5 |  | Unresolved
2 | 3 |  | Upload | Upload function current not working. |  | 2018-10-20 | Li Kai |  |  | Critical | 10 |  | Unresolved
3 | 3 |  | Upload | When no files are being choosen, the system redirect to an error page instead of prompting an error message |  | 2018-10-20 | Li Kai |  |  | High | 5 |  | Unresolved
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35