## Bug Metric
Iteration | Number of Bugs | Number of Low Impact | Number of High Impact | Number of Critical Impact | Bug Metric | Action Done | Severity | Description
1 | 0 | 0 | 0 | 0 | 0 | Nil | Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
2 | 0 | 0 | 0 | 0 | 0 | Nil | High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
3 | 3 | 0 | 2 | 1 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project. | Critical Impact (10 points) | The system is down or is usable after a short period of time. We have to fix the bugs to continue.
4 | 3 | 1 | 0 | 2 | 21 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
5 | 1 | 1 | 0 | 0 | 1 | Fix during buffer time only. | Points Calculation: Total = 1 x num (low) + 5 x num (high) + 10 x num (critical)
6 | 2 | 1 | 0 | 1 | 11 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
7 | 2 | 0 | 0 | 2 | 20 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
8 | 1 | 0 | 0 | 1 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project. | Points in Iteration | Action
9 | 3 | 1 | 1 | 1 | 16 | Stop current development and resolve the bug immediately. Project Manager reschedules the project. | Points=<5 | Fix during buffer time only.
10 | 4 | 1 | 3 | 0 | 16 | Stop current development and resolve the bug immediately. Project Manager reschedules the project. | 5<Points<10 | Use the planned debugging time.
11 |  |  |  |  | 0 |  | Points>=10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
Total | 19 | 5 | 6 | 8 | 53
Iteration

## Bug Log
No. | Iteration | Git Commit ID | Function | Description | Bug Metric Cause | Date Found | Who found? | Date Solved | Time Taken | Severity (Impact) | Points Allocation | Points Accumulated Per Iteration | Status | Action
1 | 3 |  | Registration | User unable to register new account even with the givern correct inputs. |  | 2018-10-20 | Li Kai |  |  | High | 5 |  | Resolved
2 | 3 |  | Upload | Upload function currently not working. | Upload csv file contains a missing column header | 2018-10-20 | Li Kai | 2018-10-29 | 1hour | Critical | 10 |  | Resolved
3 | 3 |  | Upload | When no files are being choosen, the system redirect to an error page instead of prompting an error message | No error checking | 2018-10-20 | Li Kai | 2018-10-21 | 30min | High | 5 |  | Resolved
4 | 4 |  | Upload | Upload function currently not working. |  | 2018-11-04 | Li Kai |  |  | Critical | 10 |  | Resolved
5 | 4 |  | Export | Export function currently not working. |  | 2018-11-04 | Li Kai | 2018-12-14 | 2hour | Critical | 10 |  | Resolved
6 | 4 |  | Table output | Table output doesn't have a table header. |  | 2018-11-04 | Li Kai | 2018-12-14 | 30min | Low | 1 |  | Resolved
7 | 5 |  | Frontend | Inconsistency of font for the navigation bar |  | 2018-11-17 | Li Kai | 2018-12-15 | 15mins | Low | 1 |  | Resolved
8 | 6 |  | Data visualisation | Unable to visualise the data through the chart |  | 2018-11-30 | Li Kai | 2018-12-15 | 30mins | Critical | 10 |  | Resolved
9 | 6 |  | Frontend | Navigation bar not working |  | 2018-11-30 | Li Kai | 2018-12-15 | 15mins | Low | 1 |  | Resolved
10 | 7 |  | Data visualisation | Unable to visualise the data through the chart |  | 2018-12-14 | Li Kai | 2018-12-15 | 30mins | Critical | 10 |  | Resolved
11 | 7 |  | Export | Export function currently not working |  | 2018-12-14 | Li Kai | 2018-12-15 | 2 hours | Critical | 10 |  | Resolved
12 | 8 |  | Data visualisation | Unable to visualise the data through the chart |  | 2018-12-28 | Li Kai | 2018-12-28 | 30mins | Critical | 10 |  | Resolved
13 | 9 |  | Upload | Only able to upload from specific folder | Unable to get the correct current working directory | 2019-01-13 | Li Kai |  |  | High | 5 |  | Resolved
14 | 9 |  | Data visualisation | Unable to visualise the data through the chart |  | 2019-01-13 | Li Kai | 2019-01-13 | 1hour | Critical | 10 |  | Resolved
15 | 9 |  | Navigation bar | Both home and beyond ideas button bring user to home page |  | 2019-01-13 | Li Kai |  |  | Low | 1 |  | Resolved
16 | 10 |  | View Dataset | Viewing of weather and movement data not available |  | 2019-01-27 | Li Kai |  |  | High | 5
17 | 10 |  | View Dataset | Unable to combine datasets for some of the data source |  | 2019-01-27 | Li Kai |  |  | High | 5
18 | 10 |  | Correlation | Inventory data's variable not shown in dependant or independent variables when selected as datasource |  | 2019-01-27 | Li Kai |  |  | High | 5
19 | 10 |  | Correlation | Unable to deselect a datasource/variable |  | 2019-01-27 | Li Kai |  |  | Low | 1
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35